## Sheet1
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Home page | 2024-11-23 | 2024-12-02 | 100% | Trịnh Thành | 2024-11-30 | 2024-12-02 | 100% | Trịnh Thành | The interface is similar to the model
List page | 2024-11-25 | 2024-12-02 | 100% | Trịnh Thành | 2024-12-01 | 2024-12-02 | 100% | Trịnh Thành | Full product categories when searching for keywords
Detail product page | 2024-11-25 | 2024-12-02 | 100% | Trịnh Thành | 2024-12-01 | 2024-12-02 | 100% | Trịnh Thành | Enough product information
Sign In page | 2024-11-23 | 2024-12-02 | 100% | Trịnh Thành | 2024-12-01 | 2024-12-02 | 100% | Trịnh Thành | Enough input to sign in
Admin page | 2024-11-21 | 2024-12-02 | 100% | Thư Võ | 2024-12-01 | 2024-12-02 | 100% | Thư Võ | Enough input data
Admin Login page | 2024-11-21 | 2024-12-02 | 100% | Thư Võ | 2024-12-01 | 2024-12-02 | 100% | Thư Võ | Allows admin to manage all data
API task | 2024-11-21 | 2024-12-02 | 100% | Trịnh Thành, Thư Võ | 2024-12-01 | 2024-12-02 | 100% | Trịnh Thành, Thư Võ | All called APIs are available
API task update | 2024-11-21 | 2024-12-02 | 100% | Thư Võ | 2024-12-01 | 2024-12-02 | 100% | Thư Võ | No error occurred when updating API data